## Quality of Life - Community Cha
2024-25 Work Plan
Maintain Quality of Life and Community Character
Better leverage healthy relationships with community members and maintain rural atmosphere in Town
Mandated/Budgeted | KEY PROJECTS/INITIATIVES | KEY OUTCOME | MILESTONES | QUARTER OF COMPLETION | LEAD DEPARTMENT | COMMITTEE INVOLVEMENT
| Senate Bill 9 (SB-9) Ordinance Review and Amendments | The Town will maintain a compliant and effective local SB-9 ordinance. |  |  | CDD
| Historic Landmark Application for the Water Tower (NEW-Post January 2025 addition) | Create a Landmark Designation for the Fremont Hills Country Club Water Tower |  |  | CDD | History
TBD | Our Town Publication | Phase out The Quarterly and increase Our Town to four issues a year | Coordinate with Our Town for the switch | 2 2025 | CMO
| Water Conservation (WELO) | The Water Efficient Landscape Ordinance (WELO) aims to promote water conservation through sustainable landscaping practices. Following a presentation from the Purissima Hills Water District, the EDPC recommended adjusting the WELO Water Conservation Factor to reduce water allocation for new landscapes, aligning it with current usage trends and promoting more efficient irrigation technologies. | Planning Commission and City Council, 1st and 2nd ordinance reading | 2 2025 | CDD | Environmental Initiatives/Environmental Design and Protection
$ $100K | Housing Element Amendment | Engage residents and amend the Housing Element | Work with the Ad Hoc Housing Element Committee to amend the certified Housing Element | 4 2025 | CDD
$ $500K | Housing Element Programs | Objective Design Standards Zoning Ordinance (multi-family) CEQA List of Ordinances: A-6 B6 E-2,3,4, and 5 E-1 A-4 E-8 B-15 B-16 B-11 B1 A-2 Pre Approved ADU plans Education, Outreach, and info exchange for housing resources (A-9, A-11, A-14, F-2, F-3, F-4, F-5, F-6, G-1, G-2, G-3, and G-4) | Objective Design Standards (Multi-Family): Establishment of methodology; creation of draft document | 1 2026 | CDD | Environmental Design and Protection/Open Space
|  |  | Zoning Ordinance (Multi-Family): Creation of draft document | 1 2026
|  |  | CEQA (Multi-Family): Creation of draft document | 1 2026
|  |  | Inclusionary Housing / Feasibility (A-6): Identify relevant example policies; craft draft policy | 1 2026
|  |  | By-right Approval Ordinance (A-4): Creation of draft document | 1 2026
|  |  | SB 35 and SB 330 Application Streaming Procedure (B1): Identify relevant example policies; craft draft policy | 1 2026
|  |  | Story Pole Policy - Ordinance Update (B-16): Identify relevant example policies; craft draft policy | 3 2025
|  |  | Density Bonus Ordinance and Incentives for ELIs (E-1): Identify relevant example policies; craft draft policy | Ongoing
|  |  | No Net Loss Monitoring (A-2): Identification of project and permit tools to assess activity against existing inventory | Ongoing
|  |  | Farmworker and Employee Housing Ordinance (E-8): Identify relevant example policies; craft draft policy (COMPLETE) | 1 2025
|  |  | Pre-approved ADU Plans: Develop standards for pre-approval of ADUs (COMPLETE) | 1 2025
|  |  | Streamline Committee Review Process - Ordinance Update (B-15) - Ordinance Update: Work with committees to identify review parameters; craft draft process for review by all committees (COMPLETE) | 3 2024
|  |  | Education, Outreach, and Information Exchange for housing resources (A-9, A-11, A-14, F-2, F-3, F-4, F-5, F-6, G-1, G-2, G-3, and G-4): Establish scope/parameters for each task; identify relevant examples; prepare outline to execute programs (COMPLETE) | 3 2024
|  |  | ADU Ordinance Update (B6): Creation of draft document (COMPLETE) | 2 2024
|  |  | Emergency Shelter/LBNC/Residential Care Ordinance Update (E-2,3, 4, and 5): Identify relevant example policies; craft draft policy (COMPLETE) | 2 2024
|  |  | Grading Ordinance Update (B-11): Creation of draft document (COMPLETE) | 1 2024
$ $150K | Community Building through Town-wide Events and Activities | Host a diverse and robust set of special events/programming that brings the community together. | Host community events throughout the year | Ongoing |  | Community Relations/Parks, Recreation & Community Events
|  |  | Continue to produce the activity guide 2x a year | Ongoing
LEGEND
$ | New Budget Resources Required

## Public Safety
2024-25 Work Plan
Promote Public Safety
Maintain the high level of public safety in the Town
Mandated/Budgeted | KEY PROJECTS/INITIATIVES | KEY OUTCOME | MILESTONES | QUARTER OF COMPLETION | LEAD DEPARTMENT | COMMITTEE INVOLVEMENT
| Establish Ad Hoc Committee: Expiring Law Enforcement Agreement with SCC Sheriff’s Office (NEW) | Engage in a new contract with the Sheriff's Office | Discuss City Council direction on key issues | 3 2025 | CMO
|  |  | Engage new contract with Sheriff's office | 2 2026
TBD | Wildfire Hazard Mitigation including HIZ (Home Ignition Zone) | Maintain compliance with California State fire policy and focus on reducing wildfire risks by modifying the immediate surroundings of a property to prevent ignition from embers and radiant heat | possible code amendment | 4 2025 | CDD | Emergency Preparedness and Response
$ ~$130K | Emergency Communication items from the EPRC (Sound Study, ALERT SCC) | Improve the Town's emergency response framework | Improve usage of AlertSCC as our primary emergency mass notification system, | 4 2025 | CMO | Emergency Preparedness and Response
|  |  | Mobilize initiative to recognize LAH emergency action leaders | 4 2025
|  |  | Establish an alternate emergency communications network | 4 2025
|  |  | Implement audible alerts to augment emergency notification | 2 2026
$ $50K | Complete Safety Element | Have a completed GP Element | Creation of a Draft Document | 4 2025 | CDD | Emergency Preparedness and Response
| Emergency Preparedness | Keep the Town Safe and prepared for emergencies | Update the EOP | 4 2025 | CMO | Emergency Preparedness and Response
|  |  | Update the Evacuation Annex | 4 2025
|  |  | Install redundant ISP to Town Hall | 4 2024
LEGEND
$ | New Budget Resources Required

## Service Delivery - Governance
2024-25 Work Plan
Increase Effective Service Delivery & Governance
Advance Town operations to better serve the community
Mandated/Budgeted | KEY PROJECTS/INITIATIVES | KEY OUTCOME | MILESTONES | QUARTER OF COMPLETION | LEAD DEPARTMENT | COMMITTEE INVOLVEMENT
| Accessory Dwelling Unit Ordinance Annual Update | Annual updates to the ADU ordinance |  |  | CDD
$ ~$20K | Upgrade the Town's Website | Refresh the Town's website with CivicPlus | Increase ease of navigation on the Town's Website | 4 2025 | CMO
| Expired Permit Management | Conduct an assessment of expired Town permits | Come up with a solution to handle ongoing permits in Town to catch them before they expire | 4 2025 | CDD
| Continue Employee Enhancement & Retention Program + Onboarding new employees | Maintain Employees | Check-in on Cultural Reset Items - Stay Interviews + new round | 2 2025 | CMO
|  |  | Conduct Development Conversation Training | 2 2024
$ $20K | Explore an Agenda Management System | Streamline the agenda process | Determine if the need for software exists (COMPLETE) | Ongoing |  | Technology
|  |  | Determine if the existing Civic Clerk or Laserfiche can be used | 2 2025
|  |  | Research agenda management systems and select one | 3 2025
$ $20K | New Building Permit Fee Schedule | Update the Town's Building Fee Schedule in line with the new COS Study | Solicit consultant support, execute contract to prepare draft Fee Schedule | 2 2025 | ASD | Finance and Investment
|  |  | Update Fee Schedule and present to FIC and City Council | 3 2025
$20K | Cost for Service Study | Complete a Cost of Service Study which is the basis to evaluation new fees | Solicit consultant support, execute contract to prepare Study | 1 2025 | ASD | Finance and Investment
|  |  | Complet Cost of Service Study and Cost Allocation Plan | 2 2025
|  |  | Present final Cost of Service Study to FIC and City Council | 3 2025
$ $20K | Maximize functions of ERP system and change to online payment | Internal Control | Use and streamline functions of ERP system (Budget/Project Accounting/Purchasing/AP/Fixed Asset) | null 2025 | ASD
|  |  | Change method of payment to vendors from paper check to EFT/Direct Deposit/BillPay by integrating with ERP system | 2 2025
$ $17K | Green House Gas Inventory | Complete a Green House Gas Inventory to track GHG Emissions | Partner with EIC and CSG for completion of GHG Inventory | Ongoing | CDD | Environmental Initiatives
| Reach Codes 2025 | Adopt new reach codes for 2025 Code Cycle |  |  | CDD | Environmental Initiatives
$ $10K | Heat Pump Rebates | Promote the use of heat pumps | Continue to offer rebates for the instillation of Heat Pumps | Ongoing | CDD | Environmental Initiatives
$ $20K | Impact Fees Assessment | Complete an assessment of current impact fees as the basis to assess whether new or revised fees are warranted | Prepare draft fee study | 4 2025 | CDD | Finance and Investment
| Historic Preservation Process Update | Increased transparency and effectiveness of Planning and Building staff regarding historic preservation efforts | HC to prepare draft policy/processes; CDD to review and suggest edits needed to integrate into GP and Muni Code | 4 2025 | CDD | History
| GIS Updates | Increased accuracy and efficiency from Planning Staff; satisfaction of HCD requirements | Creation of Document | 2 2026 | CDD
$ $25K | Land Use Element Updates | Align Land Use Element with proposed multifamily zoning and objective design standards as a part of Housing Element program A-1. | Creation of Document | 4 2025 | CDD | Pathways/Environmental Design and Protection/Open Space
|  |  | Added as a City Council workplan priority in 2025. | Ongoing
$ $130K | TRAKiT & eTRAKiT Upgrades | Increased efficiency from Planning and Building Staff | Ownership record maintenance | Ongoing | CDD
|  |  | Trakit GIS integration | 3 2025
|  |  | Trakit GIS integration | 2 2025
|  |  | Trakit Fee Schedule Indexing (COMPLETE) | 2 2025
|  |  | Trakit Automated Scheduling (online) (COMPLETE) | 2 2025
|  |  | CLSB integration (COMPLETE) | 1 2025
|  |  | Trakit Upgrade (COMPLETE) | 1 2025
|  |  | Electronic Plan Storage (COMPLETE) | 3 2024
|  |  | Trakit Electronic Submittals (COMPLETE) | 3 2024
LEGEND
$ | New Budget Resources Required

## Infrastructure
2024-25 Work Plan
Protect and Maintain Infrastructure
Maintain and expand Town assets through new technology and processes
Mandated/Budgeted | KEY PROJECTS/INITIATIVES | KEY OUTCOME | MILESTONES | QUARTER OF COMPLETION | LEAD DEPARTMENT | COMMITTEE INVOLVEMENT
$ May need budget pending number of signs needed. | Bike Advisory Signages for Pathways (NEW-Post January 2025 addition) | Safer pathways for all. | Recommendation from Pathways Committee | 3 2025 | PW/E | Pathways
|  |  | Install advisory signs | 4 2025
| Three Year Information Technology Strategic Plan (NEW-Post January 2025 addition) | Have a plan adopted by end of 2025 |  |  | CMO | Technology
| Los Altos Hills Community Fiber Installation (NEW-Post January 2025 addition) | Install Los Altos Hills Community Fiber infrastructure near Town Hall on Fremont Road, Stonebrook/Prospect/La Loma, and Stonebrook to ARK. | Issue Encroachment Permits for the work | 3 2025 | PW/E | Technology
|  |  | Oversee installation of LAHCF infrastructure | 4 2025
$ $350k | Miscellaneous Pathways | Installation of Pathways per the Town's Master Paths Plan. |  |  | PW/E | Pathways
$370k | Magdalena Avenue Pathway Project | Installation of 2,000 linear foot 2B Pathway along Magdalena Avenue from Camino Hermoso Drive. | Survey Staking | 2 2025 | PW/E | Pathways
|  |  | Design | 4 2025
|  |  | Construction | 3 2026
| Fleet & Equipment Procurement | Replace old trucks and equipment per Town policies. | Replace Ford F250 | 2 2025 | PW/E
|  |  | Replace Dodge Dakota/Superintendent Truck w/ Electric Vehicle (Lease or Buy) | 1 2026
$374,044 | Westwind Community Barn Improvements | Westwind Community Barn Improvement | Lower Arena repair | 3 2025 | PW/E
|  |  | Upper Arena Repair | 3 2025
|  |  | Paddock Repair | Ongoing
| Purissima Park Improvement Program | Purissima Park Improvements | Fence repair for Fields 1, 2, & 4 | 4 2025 | PW/E
|  |  | Parking lot maintenance | 3 2025
| Town Hall Facility Security Camera Upgrade | Bring all Town facility secuity systems under one platform | Town Hall | 4 2025 | CMO | Technology
|  |  | Corp Yard | 4 2026
|  |  | Westwind Barn | 4 2027
|  |  | Project was brought before the Technology Committee and approved by the Technology Committee in May 2025 | null 2025
|  |  | Project will be presented to City Council by Q4 2025 | 4 2025
| Civic Center Improvements/Parks & Rec Center Renovation | Finalize recommendation and obtain direction from Council; Increased workspace for Town Staff to address community needs | Obtain Council direction | 2 2024 | PW/E
|  |  | Design | 1 2026
|  |  | Construction | 4 2026
| Undergrounding Utilities - El Monte Rule 20A | Finalize design and construction for the El Monte Fire Station Undergrounding Project (Rule 20A) | Design (completed) | 1 2024 | PW/E
|  |  | Construction | 3 2025
$1,559,966 | Matadero Creek Restoration and Bank Stabilization Project | Complete Matadero Creek Erosion Project Mitigation Measures for the Matadero Creek Erosion Project | Mitigation Measures | 1 2025 | PW/E
|  |  | Construction | 3 2025
|  |  | Mitigation Measure - Monitoring | Ongoing
$900,000 | Sewer Rehabilitation and Repair | 2025 Sewer CIP | Design | Ongoing | PW/E
|  |  | Construction | 3 2025
| Corporation Yard Improvements | Corporation Yard Improvements | Master Plan Study | 2 2025 | PW/E
|  |  | Purchase and Install Conex box for storage | 2 2025
|  |  | Design - Locker Room Improvements Phase 1 | 2 2025
|  |  | Construction - Locker Room Improvements Phase 1 | 4 2025
| Heritage House Remodel | Improve Heritage House for multi-purpose use | Design | 3 2024 | PW/E | History/Emergency Preparedness and Response
|  |  | Secure Funds for Construction | 3 2024
|  |  | Construction | 4 2025
| Annual Pavement Rehabilitation and Drainage Improvement | FY2026 Street Repair Project | Design | 1 2026 | PW/E
|  |  | Construction | 3 2026
| Asset Management for Storm Drain System | To better manage, maintain, and improve the storm drain system | Storm asset information gathered | 3 2025 | PW/E
| Continue Replacement of Road Signage across the Town | Meet State’s reflective code requirement | Sign replacement | Ongoing | PW/E
$ $200K-$300K | Middle Fork to Maple Leaf Court Pathway | Construct Middle Fork to Maple Leaf Court Path | CEQA - Initial Study | 1 2026 | PW/E | Pathways
|  |  | Update Master Paths Plan | 1 2026
|  |  | Design/Environmental - TBD | Ongoing
|  |  | Construction - TBD | Ongoing
| Pathway Fee Nexus Study | Update the pathway fee and develop long-term Pathways Improvement Plan | Complete fee nexus study | 2 2025 | PW/E | Finance and Investment/Pathways
|  |  | Pathway Impact Fee Update | 4 2025
|  |  | Develop long-term plan for pathways | 2 2026
$300-450K | Summerhill Avenue Pathway - Phase II | Construct Summerhill Pathway, Phase II. | Design | 3 2025 | PW/E | Pathways
|  |  | Obtain encroachment permit from Santa Clara County and City of Los Altos | 1 2026
|  |  | Construct Phase 2 | 3 2026
LEGEND
$ | New Budget Resources Required